## Main
Scrum Project
Product | DocuPulse: An AI-Assisted Phygital Document Tracking System |  | Product Status | In Development
Active versions | v0.1 (Sprint Plan / Pre-release) |  | Sponsor | Asia Pacific College - School of Computing and Information Technologies
Team
Scrum Master | Jose Javier S. Mirador |  | Product Owner | Anthony Duenas
Developers | Kirsten Evan Pimentel |  | Project Champion | Sir. Edward Madac (Adviser/Co-Adviser)
| Aleksej Aidan Hamer |  | Other Stakeholders | Logistics
| John Adrian Ochoa |  |  | Finance
ITRO
BMO
Library
Department Heads
Executive Director
AI System
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | DocuPulse Platform Development (AY 2026-2027) | 2026-08-24 | 2026-11-27 | In Progress | Phase 1-2 (Planning & Design, Weeks 1-4) complete; Sprints 1-4 below cover Phase 3-5 (Core Dev, AI/Phygital Integration, Testing & Deployment) | Spr. 1 | 2026-09-21 | 2026-10-02 | Not Started | 50 |  | Requisition Form Submission (validation, attachments, history) and Requisition Tracking & Status Monitoring (real-time status, approval chain visibility, QR sync, Dept Head notifications) (EP-01, EP-02)
[6 empty] | Spr. 2 | 2026-10-05 | 2026-10-16 | Not Started | 28 |  | Digital Approval Workflow (Dept Head/Librarian, Finance, Logistics decisions) and Dashboard & User Management (centralized dashboard, roles/permissions) (EP-03, EP-05)
[6 empty] | Spr. 3 | 2026-10-19 | 2026-10-30 | Not Started | 47 |  | AI Features & Automation (Smart Tagging, Predictive Analytics, Anomaly Detection, Smart Flow Rerouting) and Budget & Analytics (utilization dashboards, financial impact, bottleneck reports) (EP-04, EP-06)
[6 empty] | Spr. 4 | 2026-11-02 | 2026-11-13 | Not Started | 37 |  | Notifications & Communication (status alerts, escalation) and Workflow Automation (auto-advance), plus end-to-end QA/usability testing, bug fixing, and deployment to APC hosting (EP-07, EP-08, QA, Deployment)
[6 empty] | Buffer week | 2026-11-16 | 2026-11-27 | Not Started | 0 |  | Institutional rollout buffer: stakeholder training, documentation handover, and go-live support (Week 13)
Formulas:
Project #1 = [Start]+11
Start = [Project #1, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Co-owner/Secondary Lead | Status | Remarks
DP-00 | User Authentication & Account Creation | user | create an account and sign into DocuPulse | I can access the platform according to my assigned department role | 1. Users can register with valid institutional credentials and select their department. 2. Form validates password requirements, department selection, and terms agreement. 3. Upon registration, default Requestor or assigned role is assigned. | Foundational Auth / Prerequisites for Requisition Workflows | High | In Progress | Feature | 1 | 1 | 3 |  | John Adrian Ochoa |  | In Progress
DP-01 | EP-01 Requisition Form Submission | requestor | submit a requisition form digitally | I no longer need to process requests manually | 1. Given an authorized requestor is logged into DocuPulse. 2. When they fill in all required fields and submit a new requisition form. 3. Then the system assigns a unique requisition ID, records a submission timestamp, and displays a confirmation message. | Covers Use Case 1: Manage Requisition | High | In Progress | Feature | 1 | 1 | 8 |  | Jose Javier S. Mirador |  | In Progress
DP-02 | EP-01 Requisition Form Submission | requestor | the system to validate my requisition form automatically | errors can be corrected before processing | 1. System checks completeness of submitted requisition forms. 2. Missing information is highlighted. 3. Duplicate submissions are flagged. 4. Valid requisitions proceed to Department Head approval. | Entry-level validation reduces repetitive rerouting | High | In Progress | Feature | 1 | 1 | 5 |  | Jose Javier S. Mirador |  | In Progress
DP-03 | EP-01 Requisition | requestor | attach supporting documents | my requisition submission is complete | 1. Multiple supporting files can be uploaded. 2. Supported formats include |  | Medium | Done | Feature | 1 | 1 | 3 |  | Anthony Duenas |  | In Progress
DP-04 | EP-01 Requisition Form Submission | requestor | view my previous requisition forms | I can reference past requests | 1. Dashboard shows submitted requisitions. 2. Requisitions are searchable. 3. Users can view current and historical statuses. |  | Medium | In Progress | Feature | 1 | 1 | 5 |  | Aleksej Aidan Hamer | John Adrian Ochoa | In Progress
DP-05 | EP-02 Requisition Tracking & Status | requestor | track my requisition form in real time | I know its current status | 1. Current workflow stage is visible. 2. Current department handling the requisition is displayed. 3. Updates appear within one minute of status |  | High | In Progress | Feature | 1 | 1 | 8 |  | Kirsten Evan Pimentel |  | In Progress
DP-06 | EP-02 Requisition Tracking & Status | requestor | see the approval chain of my requisition form | I know where delays occur | 1. Department Head approval status is visible. 2. Finance approval status is visible. 3. Logistics processing status is visible. 4. Date and time of each action |  | High | In Progress | Feature | 1 | 1 | 5 |  | Kirsten Evan Pimentel |  | In Progress
DP-07 | EP-02 Requisition Tracking & Status Monitoring | logistics staff member | scan QR codes attached to requisition forms | physical and digital records remain synchronized | 1. QR code is generated upon submission. 2. QR scans update requisition location. 3. Updates are timestamped. 4. Tracking location updates in the system upon successful | Core to the phygital tracking concept | High | In Progress | Feature | 1 | 1 | 8 |  | Anthony Duenas |  | In Progress
DP-08 | EP-02 Requisition Tracking & Status Monitoring | Department Head | review requisition forms | only authorized requests proceed to Finance | 1. Notifications are generated automatically. 2. Current stage is included in the notification. 3. Notification history is stored. |  | High | In Progress | Feature | 1 | 1 | 5 |  | Aleksej Aidan Hamer | John Adrian Ochoa | In Progress
DP-09 | EP-03 Digital Approval Workflow | Department Head / Librarian | review and digitally approve or reject requisition forms | I do not need to be physically present to sign | 1. Pending requisitions appear in the approval queue. 2. Supporting documents are visible. 3. Department Head can approve or reject. | Librarian applies exclusively to library acquisition/guidance requisitions | High | To Do | Feature | 1 | 2 | 5 |  | Aleksej Aidan Hamer |  | To Do
DP-10 | EP-03 Digital Approval Workflow | finance officer | review the budget impact before approving a requisition form | overspending can be prevented | 1. Budget utilization is displayed. 2. Estimated cost is displayed. 3. Finance may approve, reject, or place on hold. 4. Approved requisitions move to Logistics. 5. Requests exceeding budget are |  | High | To Do | Feature | 1 | 2 | 5 |  | John Adrian Ochoa |  | To Do
DP-11 | EP-03 Digital Approval Workflow | logistics officer | process approved requisitions | procurement activities can begin | 1. Logistics receives approved requisitions. 2. Processing remarks may be recorded. 3. Status updates are logged. 4. Requestor receives updates. |  | High | To Do | Feature | 1 | 2 | 5 |  | Jose Javier S. Mirador |  | To Do
DP-12 | EP-04 AI Features & Automation | Department Head | requisitions automatically categorized with smart tags | I can quickly filter and review requests | 1. The system automatically assigns tags based on requisition type. 2. Tags are generated upon submission. 3. Tags are visible to Department Heads, Finance, and Logistics. 4. Authorized users can manually correct incorrect tags. | AI capability: Smart Tagging | High | To Do | Feature | 1 | 3 | 8 |  | Anthony Duenas |  | To Do
DP-13 | EP-04 AI Features & Automation | Finance Officer | view AI-generated budget impact estimates | I can make informed approval decisions before committing funds | 1. The system estimates the projected cost of the requisition. | AI capability: Predictive Analytics | High | To Do | Feature | 1 | 3 | 8 |  | Kirsten Evan Pimentel |  | To Do
DP-14 | EP-04 AI Features & Automation | Finance Officer | duplicate or unusual requisitions flagged automatically | potential errors and improper requests are caught early | 1. The system automatically checks for duplicate submissions. 2. The system identifies unusual request patterns. 3. Duplicate requisitions are flagged before approval. | AI capability: Anomaly Detection | High | To Do | Feature | 1 | 3 | 8 |  | Aleksej Aidan Hamer |  | To Do
DP-15 | EP-04 AI Features & Automation | Approver (Department Head / Executive Director) | high-cost or high-risk requisitions automatically rerouted for additional senior review | major expenses undergo proper oversight | 1. The system evaluates requisitions using cost and anomaly indicators. 2. High-cost requisitions are flagged automatically. 3. High-risk requisitions are redirected to additional authorized reviewers. 4. Rerouting decisions are logged with timestamps. 5. Requestors and reviewers are notified when rerouting occurs. | AI capability: Smart Flow Rerouting | High | To Do | Feature | 1 | 3 | 8 |  | John Adrian Ochoa |  | To Do
DP-16 | EP-05 Dashboard & User Management | logistics staff member | a centralized dashboard showing all requisitions | I can monitor institution-wide workflow activity | 1. Dashboard displays all active requisitions. 2. Requisitions can be filtered by status and department. 3. High-priority requisitions are highlighted. 4. Dashboard displays current workflow stage. 5. Dashboard refreshes active queue data upon status change. |  | High | To Do | Admin | 1 | 2 | 8 |  | Jose Javier S. Mirador |  | To Do
DP-17 | EP-05 Dashboard & User Management | logistics staff | manage user roles and permissions | users only access information relevant to their responsibilities | 1. Administrator can create user accounts. 2. Administrator can edit user information. 3. Administrator can deactivate accounts. 4. Role permissions are configurable. 5. Access changes take effect immediately. |  | High | To Do | Admin | 1 | 2 | 5 |  | Anthony Duenas |  | To Do
DP-18 | EP-06 Budget & Analytics | finance officer | visualize budget utilization | spending can be monitored effectively | 1. Dashboard displays total approved expenditures. 2. Remaining budget is displayed. 3. Budget utilization is represented visually. 4. Data can be viewed per department. 5. Historical budget records can be accessed. |  | High | To Do | Feature | 1 | 3 | 5 |  | Kirsten Evan Pimentel |  | To Do
DP-19 | EP-06 Budget & Analytics | finance officer | see the financial impact of each requisition | approvals are based on available funds | 1. Estimated requisition cost is displayed. 2. Budget impact is calculated automatically. 3. Finance personnel can compare cost against remaining budget. 4. Budget warnings appear when limits are approached. 5. Cost analysis is recorded in the requisition history. |  | High | To Do | Feature | 1 | 3 | 5 |  | Aleksej Aidan Hamer |  | To Do
DP-20 | EP-06 Budget & Analytics | logistics staff | reports on processing times and workflow bottlenecks | process improvements can be identified | 1. Reports show average processing times. 2. Reports identify delayed requisitions. 3. Reports can be filtered by department. 4. Reports can be exported. 5. Historical reports are retained. |  | Medium | To Do | Admin | 1 | 3 | 5 |  | John Adrian Ochoa |  | To Do
DP-21 | EP-07 Notifications & Communicatio n | requestor | notifications for every workflow stage change | I know the progress of my requisition | 1. Notifications are generated automatically on status changes. 2. Notifications indicate the new workflow stage. 3. Notifications are visible in-app. 4. Notification history is maintained. 5. Users can view previously received notifications. |  | High | To Do | Feature | 1 | 4 | 3 |  | Jose Javier S. Mirador |  | To Do
DP-22 | EP-07 Notifications & Communicatio n | requestor | escalation alerts when a requisition is delayed | bottlenecks are visible | 1. The system identifies delayed requisitions. 2. Escalation alerts are automatically generated. 3. Alerts include the current workflow stage. 4. Alerts indicate the number of delayed days. 5. Escalation events are recorded in the system. |  | Medium | To Do | Feature | 1 | 4 | 5 |  | Anthony Duenas |  | To Do
DP-23 | EP-08 Workflow Automation | Requestor | my requisition to automatically advance to the next approval stage upon review | processing continues without manual handoffs | 1. Approved Department Head requisitions move automatically to Finance. 2. Approved Finance requisitions move to Logistics. 3. Rejected requisitions stop the workflow. 4. Workflow transitions are timestamped and logged. 5. Requestors receive notifications after each workflow transition. |  | High | To Do | Feature | 1 | 4 | 8 |  | Kirsten Evan Pimentel |  | To Do
DP-24 | QA / Usability & Functional Testing | project team | conduct end-to-end functional and usability testing across all core workflows | the platform meets functional requirements before institutional rollout | Given all Sprint 1-4 features are complete, when usability testing is conducted with representative requestors and approvers, then the system passes functional test cases and achieves an acceptable usability score. | Covers Requisition Submission, Tracking, Approval, and AI features end-to-end | High | To Do | QA | 1 | 4 | 8 |  | Aleksej Aidan Hamer |  | To Do
DP-25 | QA / Bug Fixing | project team | fix defects identified during testing | the system is stable and ready for production use | Given a logged defect, when the team resolves and retests it, then the issue no longer reproduces and is marked closed. | Prioritize blockers/high-severity issues first | High | To Do | QA | 1 | 4 | 8 |  | John Adrian Ochoa |  | To Do
DP-26 | Deployment | ITRO / Logistics team | deploy DocuPulse to the APC hosting environment | the system is accessible to all departments campus-wide | Given a stable, tested build, when the team deploys the Web Portal, Requisition API, and databases to hosting (e.g., Promox and Supabase), then the platform is reachable by all authorized users without errors. | No dedicated mobile app; responsive web only | High | To Do | Deployme nt | 1 | 4 | 5 |  | Jose Javier S. Mirador |  | To Do

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Co-Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1 | DP-00 | User Authentication & Account Creation | John Adrian Ochoa |  | Done | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1
1 | DP-01 | Submit requisition form digital | Jose Javier S. Mirador |  | Done | 8 | 8 | 8 | 4 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
1 | DP-02 | Automatic requisition form | Jose Javier S. Mirador |  | Done | 5 | 5 | 5 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0
1 | DP-03 | Attach supporting documents | Anthony Duenas |  | Done | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
1 | DP-04 | View previous requisition | Aleksej Aidan Hamer | John Adrian Ochoa | Done | 5 | 4 | 5 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DP-05 | Real-time requisition status | Kristen Evan Pimentel |  | Done | 8 | 8 | 8 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 0
1 | DP-06 | View approval chain of requisition | Kristen Evan Pimentel |  | Done | 5 | 5 | 5 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
1 | DP-07 | QR code scan for phygital sync | Anthony Duenas |  | Done | 8 | 8 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0
1 | DP-08 | Department Head review notification | Aleksej Aidan Hamer | John Adrian Ochoa | Done | 5 | 5 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
2 | DP-09 | Review & digitally approve/reject requisition forms | Aleksej Aidan Hamer |  | To Do | 5 | 0 | 5
2 | DP-10 | Review budget impact before approving requisition | John Adrian Ochoa |  | To Do | 5 | 0 | 0
2 | DP-11 | Process approved requisitions (Logistics) | Jose Javier S. Mirador |  | To Do | 5 | 0 | 5
2 | DP-16 | Centralized requisition dashboard | Jose Javier S. Mirador |  | To Do | 8 | 0 | 8
2 | DP-17 | Manage user roles & permissions | Anthony Duenas |  | To Do | 5 | 0 | 5
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
|  |  |  | Total | 78 | 49 | 57 | 22 | 0 | 6 | 2 | 4 | 0 | 6 | 5 | 2 | 2
|  |  |  | Burn down |  |  |  | 56 | 56 | 50 | 48 | 44 | 44 | 38 | 33 | 31 | 29
|  |  |  | Burn up |  |  |  | 22 | 22 | 28 | 30 | 34 | 34 | 40 | 45 | 47 | 49

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks
IMP-01 | Delay starting Sprint 1 tasks due to unassigned task owners and uncalibrated DP story point estimates. | Aleksej Hamer | 2026-09-15 | Sprint 1 | DP-01 to DP-08 | Aleksej Hamer | Closed | Held a backlog refinement meeting to assign owners and calibrate story points. | 2026-09-16 | Backlog finalized and ownership clarified across the team.
IMP-02 | Initial confusion regarding the end-to-end user workflow and specific requirements for each DP. | Team | 2026-09-17 | Sprint 1 | DP-01 to DP-08 | Aleksej Hamer | Closed | Reviewed System Use Case Specifications together and mapped out all stage transitions. | 2026-09-18 | Requisition workflow logic aligned across frontend and backend.
IMP-03 | Delay in starting frontend component coding due to missing Figma wireframes and design system. | Team | 2026-09-18 | Sprint 1 | DP-01, DP-04 | Team | Closed | Finalized component layouts, color palettes, and UI prototypes in Figma. | 2026-09-20 | UI design system established; frontend coding commenced smoothly.
IMP-04 | Configuration issues connecting backend environment variables, Supabase database, and API routing. | Jose Javier S. Mirador | 2026-09-21 | Sprint 1 | DP-02, DP-08 | Jose Javier S. Mirador | Closed | Set up proper API keys, database tables, and NestJS adapter routing. | 2026-09-23 | Backend structure stabilized and database connectivity verified.

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks
Sprint 1 | 2026-09-29 | Aleksej Hamer | Leading daily scrum meetings consistently and organizing team logs. | Enforcing strict meeting start times and keeping team tasks on schedule. | Allowing meetings to start late or tasks to proceed without check-ins. | Workload balanced well across the sprint.
Sprint 1 | 2026-09-29 | Jose Javier S. Mirador | Finishing assigned tasks quickly and managing repository updates. | Improving arrival time for daily team meetings. | Minor meeting tardiness | Task completion speed is high; working on meeting punctuality.
Sprint 1 | 2026-09-29 | Anthony Duenas | Assisting with backend setup and database integration. | Improving arrival time for daily team meetings. | Minor meeting tardiness | Task completion speed is alright; working on meeting punctuality.
Sprint 1 | 2026-09-29 | Kristen Evan Pimentel | Reliably completing coding tasks quickly with high quality. | Improving arrival time for daily team meetings. | Minor meeting tardiness | Task completion speed is good; working on meeting punctuality.
Sprint 1 | 2026-09-29 | John Adrian Ochoa | Assisting with testing app features and giving useful insights. | Arriving on time for all scheduled group meetings and team syncs. | Being consistently late to daily scrums and team discussions. | Testing and completion output is good; major improvement needed on meeting punctuality.

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
DocuPulse Full Project Documentation (MSYADD1) | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms | Use Case Diagram / Full Dressed Use Cases
Scrum Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/ | System Context, Container & Ccmponent
|  | Figma | https://www.figma.com/make/bkBYzmTVkSLdKEk4ctR9Jw/Document-Tracking-System?t=UW0vMv0lCwRQjHGk-1